# Public Sector Equality and Human Rights Duty

# Action Plan 2026-2027

# Introduction

## Background

All public sector bodies have a duty to eliminate discrimination, promote equality, and protect the human rights of both their staff and those to which they provide services. This obligation is set out under Section 42 of the Irish Human Rights and Equality Commission Act 2014.

Specifically, Section 42(1) of the Act states that:

“a public body shall. In the performance of its functions, have regard to the need to:

- eliminate discrimination

- promote equality of opportunity and treatment of its staff and the persons to whom it provides services, and

- protect the human rights of its members, staff and the persons to whom it provides services”

Section 42(2) of the Act requires a public body to assess the human rights and equality issues that are relevant to its functions and purpose, and to set out a plan to address these issues that is made publicly accessible. The assessment process and strategic plan should take regard of the purpose and function of the body, its size, and its available resources.

The Irish Human Rights and Equality Commission has summarised the obligation to implement the Public Sector Duty as a three-step approach:

1. Assess: Public sector bodies must assess and identify human rights and equality issues relevant to their purpose and functions. The assessment should be evidence-based, drawing on available data including the knowledge and experience of staff and service users.

2. Address: Public sector bodies must identify suitable policies, plans, or actions that are currently in place or that will be implemented in order to address the concerns identified. The body should consider the order of priority of these actions. Addressing the issues identified assists the organisation to improve outcomes for both its staff and service users.

3. Report: The public body must report to the general public, through annual reports or other documents, on developments and achievements in an accessible manner.

This new Public Sector Duty Action Plan 2026–2027 was developed following internal and external engagement and consultation. This included proactive outreach to and consultation with Disabled Persons Organisations (DPOs).

## Previous NDA Public Sector Duty Action Plans

The NDA has had two previous Public Sector Duty Action Plans. The first was developed in 2019 (approved in 2020) and ran until 2022 (a review of this action plan was conducted in late 2022). The second action plan covered the period 2024–2025.

## Monitoring of progress

Progress against the actions set out in this action plan, alongside other relevant developments, will be publicly reported through the NDA’s annual reports.

## Next steps

This action plan covers the period 2026-2027, with the intention being to realign our future action plans with the NDA’s strategic planning cycle. Preparatory work for the NDA’s next strategic plan, covering the period 2028-2030, will begin in early 2027. The development of this plan will include early consultation with stakeholders about views on gaps in relation to the NDA meeting Public Sector Duty obligations, with accessibility considerations accounted for. Our next Action Plan will cover a three-year period.

## Community safety duty

In addition to the Public Sector Human Rights and Equality Duty, the next PSD Action Plan will also incorporate requirements for public bodies relating to community safety set out in the Policing, Security and Community Safety Act 2024.

The legislation (which was commenced in April 2025) requires public bodies to assess relevant community safety issues and set out policies, plans and actions to address these in its strategic plan. It must then report on developments in relation to addressing the community safety issues identified in its annual report.

# Detailed Action Plan

## Action Area 1 – Embedding the Duty

| Action | Indicators of Achievement | Timeframe | Team responsible |
| --- | --- | --- | --- |
| 1.1 Establish a Public Sector Duty Equality and Human Rights Steering Committee | Public Sector Duty Steering Committee established Broad representation on the Public Sector Duty Steering Committee across the organisation Public Sector Duty Steering Committee meets at least once per quarter | Q3 2026 Q3 2026 Q4 2027 | Policy, Research and Public Affairs Team (with participation of CEUDSM and CSD) |
| 1.2 Develop Terms of Reference for the PSD Steering Committee | Terms of Reference for the Public Sector Duty Steering Committee developed | Q3 2026 | PSD Steering Committee |
| 1.3 Make IHREC’s ‘Equality and Human Rights in the Public Service’ eLearning course a mandatory part of the induction process | eLearning course added to induction process and materials for new starters in the NDA | Q3 2026 | Corporate Services |
| 1.4 Encourage all existing NDA staff to complete IHREC’s ‘Equality and Human Rights in the Public Service’ eLearning course | All staff to have completed the eLearning course | Q1 2027 | PSD Steering Committee |
| 1.5 Identify and communicate training opportunities and resources related to Public Sector Duty obligations to staff | Staff are aware of opportunities for training and development connected to the Public Sector Duty, such as IHREC’s Professional Diploma Course in Human Rights and Equality | Q4 2027 | PSD Steering Committee; CSD |
| 1.6 Ensure the upcoming consultation to inform the NDA Strategic Plan 2028-2030 explicitly incorporates consideration of the Public Sector Duty | The Public Sector Duty is explicitly considered as part of the consultation to inform the NDA Strategic Plan 2028-2030 | Q2 2027 | Senior Leadership Team; CSD |

## Action Area 2 – Intersectionality

| Action | Indicators of Achievement | Timeframe | Team responsible |
| --- | --- | --- | --- |
| 2.1 Organise at least two briefings for staff per year on lived experiences of people across a range of equality grounds | Two briefings on lived experiences of people across a range of equality grounds organised per annum | Q4 2027 | PSD Steering Committee (with input from CSD) |
| 2.2 Continue to consider intersectionality and the diversity of experiences of disabled people in policy and other submissions | 10 examples per year on where intersectionality has been considered in our work | Q4 2027 | Policy, Research and Public Affairs Team; CEUDSM |
| 2.3 Continue to consider intersectionality and the diversity of experiences of disabled people in research, including our Research Promotion Scheme (RPS) | Intersectionality embedded into the theme of the current RPS scheme Intersectionality considered as part of the development of future RPS schemes | Q4 2027 | Policy, Research and Public Affairs Team |

## Action Area 3 – Accessibility

| Action | Indicators of Achievement | Timeframe | Team responsible |
| --- | --- | --- | --- |
| 3.1 Publicise the availability of the NDA’s Changing Places Toilet | Information on accessing the Changing Places Toilet available on the NDA website and facility is used by the general public and visitors to the NDA | Q4 2026 | Corporate Services |
| 3.2 Develop a policy on screen reader accessible versions of documents | Policy on screen reader accessible versions of documents developed | Q4 2026 | Communications Team |
| 3.3 Make Irish Sign Language beginner course available to staff | NDA staff complete ISL beginner course | Q4 2026 | Corporate Services |
| 3.4 Provide Deaf Awareness Training to NDA staff | NDA staff receive Deaf Awareness Training | Q1 2027 | PSD Steering Committee |
| 3.5 Introduce a shortened, more accessible phone message recording | Shortened, more accessible phone message recording available | Q2 2026 | Corporate Services |
| 3.6 Review our internal procurement guidelines and incorporate guidance on Universal Design | Internal procurement guidelines reviewed and incorporate UD guidance | Q4 2026 | Corporate Services; CEUD |
| 3.7 Ensure accessibility is at the forefront of the NDA website performance, content and accessibility review | NDA website review completed, with improved accessibility Accessibility score of nda.ie checked quarterly with issues addressed | Q4 2026 Q4 2027 | Communications Team (with input from WAD team and Policy, Research and Public Affairs Team; CEUDSM; CSD) |
| 3.8 Ensure accessibility is at the forefront of the CEUD website review | CEUD website review completed, with improved navigability and accessibility Accessibility score of universaldesign.ie checked quarterly with issues addressed | Q4 2026 Q4 2027 | CEUDSM (with input from Communications Team and WAD team) |
| 3.9 Following completion of the content audit of the NDA website, review and update ISL video content, and identify content on CEUD website for translation to ISL video content | Relevant ISL video content on nda.ie reviewed and updated Relevant ISL video content added to universaldesign.ie | Q2 2027 Q2 2027 | Communications Team (with input from CEUDSM) |
| 3.10 Undertake a redesign of the Someone Like Me website, with accessibility, user journey and WAD compliance core considerations | Someone Like Me website redesigned, which fully meets WAD requirements Accessibility score of Someone Like Me website is checked quarterly with issues addressed | Q3 2026 Q4 2027 | Communications Team |
| 3.11 Encourage all staff to complete the new e-Learning module on disability equality and incorporate the new module into the NDA induction process | All staff to have completed e-Learning module on disability equality E-Learning module on disability equality incorporated into induction process | Q1 2027 Q3 2027 | Corporate Services |
| 3.12 Continue to maximise the accessibility of NDA events, including through the provision of accessibility measures and reasonable accommodations, as well as hybrid options where possible | NDA events are accessible and inclusive, with accessibility and reasonable accommodation measures provided | Q4 2027 | Policy, Research and Public Affairs; CEUDSM; Communications Team |
| 3.13 Continue to provide ISL access in communications and public services, in line with statutory requirements under the Irish Sign Language Act 2017 | ISL access is provided in line with statutory requirements under the ISL Act 2017 | Q4 2027 | Policy, Research and Public Affairs Team; CEUDSM; CSD. |

## Action Area 4 – Inclusivity in the workplace

| Action | Indicators of Achievement | Timeframe | Team responsible |
| --- | --- | --- | --- |
| 4.1 Develop an organisational People Strategy, which includes a dedicated Equality, Diversity and Inclusion goal | People Strategy developed | Q4 2026 | Corporate Services |
| 4.2 Develop a dedicated Equality, Diversity and Inclusion Strategy for the organisation | EDI strategy developed | Q2 2027 | Corporate Services |
| 4.3 Develop a reasonable accommodation policy, ensuring it is aligned with the broader approach across the Civil Service | Reasonable accommodation policy developed | Q2 2027 | Corporate Services |
| 4.4 Continue to ensure inclusive work practices through blended working arrangements as relevant and appropriate | Inclusive work practices continue to be provided through blended working arrangements | Q4 2027 | Corporate Services |
| 4.5 Establish a network of Mental Health First Aiders | Mental Health First Aiders designated and trained | Q2 2026 | Corporate Services |
| 4.6 Raise awareness regarding leave entitlements (such as parents leave, sick leave, carer’s leave), application processes, and return to work procedures | Staff are made aware and are aware of their leave entitlements, application processes and return to work procedures | Q4 2027 | Corporate Services |

## Action Area 5 – Stakeholder engagement

| Action | Indicators of Achievement | Timeframe | Team responsible |
| --- | --- | --- | --- |
| 5.1 Collate and disseminate best practice guidance for running accessible and universally designed events for internal and external stakeholders | Scoping of existing guidance completed Guidance collated and disseminated to staff | Q2 2026 Q3 2026 | Communications Team |
| 5.2 Review and update internal guidelines on consulting with Disabled Persons Organisations | Guidelines are reviewed, updated and circulated to all staff | Q1 2027 | Policy, Research and Public Affairs Team |
| 5.3 Update project management documents to include a section on consultation and feedback as a tool for staff to ensure they are considering our Participation Matters advice in their work | Project management documents updated to include a section on consultation and feedback | Q4 2026 | Corporate Services |
| 5.4 Update our advice paper on disability language and terminology in consultation with Disabled Persons Organisations and other key stakeholders | Advice paper updated and published | Q3 2026 | Policy, Research and Public Affairs Team |
| 5.5 Continue to implement the NDA’s Communications and Engagement strategy, with a focus on accessibility and reaching more diverse audiences | Annual review of communications completed and any accessibility recommendations which may arise are addressed | Q4 2027 | Communications Team |
| 5.6 Review our quarterly newsletter, with improving accessibility as a primary consideration | Newsletter reviewed and made more accessible | Q1 2027 | Communications Team |
| 5.7 Continue to ensure that NDA and CEUD consultation and engagement initiatives are accessible to stakeholders | Consultation and engagement initiatives are accessible, with accessibility and reasonable accommodation measures provided as necessary | Q4 2027 | Policy, Research and Public Affairs Team; CEUDSM |